## Costed AWP
EASTERN AND SOUTHERN AFRICA CENTERS OF EXCELLENCE (ACE II)
Name of the ACE: AQUACULTURE AND FISHERIES SCIENCE (AQUAFISH) | [9 empty] | Year 2019-2020
July 2019 - June 2020
Action Plan | Component | Sub- component | Objective | Justification | Output | DLI # | DLR # | Estimated Budget (US$) | Responsible Unit | July | August | September | October | November | December | January | February | March | April | May | June
5.1. ACE action plan to achieve Learning Excellence
| 5.1.1. Conduct tracer study |  | To collect information on marketability of the programs and employability of graduates | To help University management on restrategizing on programs and curriculum | Tracer study report to input into curriculum review |  |  |  |  | July 2019 - June 2020 July: DONE
| 5.1.2 Train regional and national students/staff on longterm training PhD and MSc (full and partial) | PhD (National 3/5) and (National MSc 3/5) | [5 empty] | 103585 | bar: July 2019 - June 2020 July to July 2019 - June 2020 October; July 2019 - June 2020 January to July 2019 - June 2020 April
| 5.1.3. Review curriculum |  | To update and enhance old curriculum | To ensure relevance of programs to current market needs | Reviewed programs meeting market needs |  |  | 75000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 February
| 5.1.4. Develop and Conduct retooling courses for staff members on e-learning tools and experiential learning |  | To equip staff on e-learning tools and experiential elarning | To ensure that staff have up to date knowledge and skills | Teaching and ICT skills enhanced | 2 | 2 | 35000 | bar: July 2019 - June 2020 August to July 2019 - June 2020 January
| 5.1.5. Enhance ICT Unit (Updating Website) |  | To develop AquaFish website |  | Website developed and functional | 2 | 2 | 10000
| 5.1.6. Recruit PhD and MSc students (full and partial) |  | To produce fit-for-purpose graduates | To contribute to human resource capacity in the sector at national and regional levels | Number of students enrolled | 2 | 2.2.3/4 | 300000
| 5.1.7. Support Academic and Technical staff for short course/internships and also staff exchange |  | To equip academic and technical staff will skills to deriver in teaching and technical services | To ensure the staff are well equipped and well conversant with their day today work | Academic and Technical staff members trained | 2 | 2 | 65000
| 5.1.8. Procure Library Resources | [6 empty] | 15000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 December
| 5.1.9. Procure a minibus |  |  | To ensure students mobilty for field work |  | 2 | 2 | 60000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 March
| 5.1.10. Purchase of equipment, chemicals and supplies |  | To equip laboratories to have adequate pieces of equipment and enough teaching and lab materials | To contribute towards teaching and learning is taking place by using latest equipment and enough supplies of lab materials including chemicals | Pieces of equipment , lab materials and chemicals procured | 2 | 2 | 107000
| 5.1.11. Rehabilitation and re-equipping of computer labs for 5 dept, AQF LT and HoDs office |  | To improve computer laboratory conditions of the university | To imporove the environment for postgraduate teaching and learning through access of well equipped computer laboratories | Computer laboratories in the participating departments improved and equipped | 2 | 2 | 25000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 October
|  | Subtotal | [5 empty] | 795585
5.2. ACE action plan to achieve Research Excellence
| 5.2.1. Develop Research agenda |  | To develop research grant for the project. | To prioritise research areas for the Centres. | Research agenda document |  |  | 0 |  | July 2019 - June 2020 July: DONE
| 5.2.2 Train PhD and MSC students in research |  |  |  | Number of student in research |  |  | 147000
| 5.2.3 Staff long term training PhD and MSc |  |  |  | Number of staff on long term training |  |  | 25000
| 5.2.4 Administer research grants to staff as seed money |  | To increase research done by staff. | To increase research outputs and quality among staff | Number of grants given to staff |  |  | 50000
| 5.2.5. Establish and operationalise (Research) MoUs with private sector |  | To increase collaboration between ACE and private centre | To increase staff and students' internship at private sector institutions | Signed memoranda of undertanding that are operational. |  |  | 0
| 5.2.6. Renovation of research facilities (ponds and tanks) |  | To renovate research facilities at the Bunda Fish Farm. | To make more facilities suitable for research use | Rnumber of ponds and tanks renovated |  |  | 38670 | bar: July 2019 - June 2020 July to July 2019 - June 2020 March
| 5.2.7. Scaling up of feed mill operations |  | To increase feed production from Bunda fish Mill. | To increase feed supply to farmers and generate income for the institution. | Bags of feed produced and sold |  |  | 14000
| 5.2.8 Publish refereed journal articles |  | To disseminate research results | To enhance relevance of science in development | number of publications produced |  |  | 8750
| 5.2.9 Scaling up best practices | [6 empty] | 16000
| 5.2.10 Conduct outreach programs | [6 empty] | 15000
| 5.2.11 Dissemination workshops | Hold dissemination workshops | [5 empty] | 30000
|  | Subtotal | [5 empty] | 314420
5.3. ACE action for Quality Assurance
| 5.3.1. Develop an e-based student tracking system |  | To develop an e-based staff performance evaluation and tracking system |  | E-based system launched |  |  | 15000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 February
| 5.3.2. Recruit external examiners |  | To improve student assessement standards and accountability | To ensure that programs maintain standards of higher education. | Offer letters |  |  | 42000 | bar: July 2019 - June 2020 October to July 2019 - June 2020 June
| 5.3.3. Support development of an external examination and supervision policies |  | To facilitate policy driven engagement in higher education | To ensure that programs maintain standards of higher education. | Policy documents |  |  | 5000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 December
| 5.3.4. Facilitate accreditation at Regional level |  | To facilitate accreditation at national level | To ensure that programs maintain standards of higher education. | Accreditation letter | bar: July 2019 - June 2020 October to July 2019 - June 2020 June
| 5.3.5. Facilitate accreditation at International level |  | To facilitate accreditation at national level | To ensure that programs maintain standards of higher education. | Accreditation letter |  |  | 70000 | bar: July 2019 - June 2020 October to July 2019 - June 2020 June
| 5.3.6. Conduct benchmarking (PASET) |  | To participate in PASET benchmarking | To ensure that programs maintain standards of higher education. | Benchmarking document |  |  | 15000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 October
|  | Subtotal | [5 empty] | 147000
5.4. ACE action for Equity Dimensions
| 5.4.1. Sensitization meetings on Gender (students and staff) |  | To mainstream gender in academic circles among staff and students | To ensure issues of gender are understood among students and staff at university level | Sensitization meetings conducted. |  |  | 22500 | bar: July 2019 - June 2020 November; July 2019 - June 2020 May
| 5.4.2. Support special scholarships for females students at MSc and PhD level |  | To mainstream gender in academic circles among MSc students | To ensure issues of gender are understood among MSc students at university level | Sensitization meetings conducted. |  |  | 46284 | bar: July 2019 - June 2020 December to July 2019 - June 2020 June
| 5.4.3. Support special needs students |  | To mainstream disablity issues in academic circles among MSc and PhD students | To ensure issues of disability are understood among PhD students at university level |  |  |  | 0
|  | Subtotal | [5 empty] | 68784
5.5. ACE action plan for Attracting Staff and Students from the Region
| 5.5.1. Advertise the programs in the region |  | To compile available information about the programs of the center for potential clients and students | To attract potential applicants to the programmes of the center and reach wider coverage with required information and on time. | Advertisements placed on website, local and international papers, in meetings and workshops, fliers produced. |  |  | 1207 | bar: July 2019 - June 2020 July to July 2019 - June 2020 September; July 2019 - June 2020 December to July 2019 - June 2020 February
| 5.5.2. Marketing the programs |  | To market the center programs by providing enough information that can reach the wider range of clients and potential students | To increase student enrolment as required and attract targetted potential clients and students | A marketing startegy in place |  |  | 30000
| 5.5.3 Staff Mobilization | [6 empty] | 10000
| 5.5.4 Remedial courses (e.g. language, stats, maths, res methods) - courses material development | [6 empty] | 15000
|  | Subtotal | [5 empty] | 56207
5.6./5.8. ACE action plan to develop National, Regional and International Academic Partnerships
| 5.6 Support teaching and leaning (adverts, staff exchange visits, Train staff from MALDECO, Train staff for UoE) | Advertise for supply of Lab & field supplies for teaching & learning materials | [5 empty] | 35334 | bar: July 2019 - June 2020 July to July 2019 - June 2020 December
|  | Conduct staff exchange visits | [5 empty] | 102000
Train one staff at MSc level from (MALDECO)
|  | Train one staff at PhD level from (UoE) | [5 empty] | 28000 | bar: July 2019 - June 2020 November to July 2019 - June 2020 June
|  | Research facilitation | [5 empty] | 0
| 5.6.1/8.1. Short term course participation |  | To equip staff with modern technologies | Science is dynamic as such retooling is critical | Number of staff attended short courses |  |  | 20000 | bar: July 2019 - June 2020 October to July 2019 - June 2020 March
| 5.6.2 Create outreach and technology transfer nodes |  | To establish outreach and technology nodes |  |  |  |  | 40000
| 5.6.2 Internships |  | To enhance staff development |  |  |  |  | 30000 | bar: July 2019 - June 2020 October to July 2019 - June 2020 June
| 5.6.2/8.2. Conference attendance |  | To enable staff disseminate their research and get exposed to cutting edge research | Networking is crucial for scientists | Number of staff attended conferences and papers in proceedings |  |  | 22000
| 5.6.3/8.3. Support publications |  | To disseminate research findings | Need for users to apply the research | Number of papers published in peer reviewed journals |  |  | 2611
|  | Subtotal | [5 empty] | 279945
5.7. ACE action plan to develop National and Regional Sector Partnerships
| 5.7.1 Teaching and learning |  | To support teaaching and learning for national and regional partners |  |  |  |  | 17666.67
| 5.7.2 Support Staff exchange visits for sector partners |  | To encourage peer learning for center staff by transfer of skills |  |  |  |  | 30000
| 5.7.3 Research facilitation (partial scholarships) |  | To enhance researach capacity for center staff |  |  |  |  | 12025
| 5.7.4 Short courses/ retooling |  | To improve sustainbale financing capacity |  |  |  |  | 16500
| 5.7.5 Outreach and technology transfer |  | To improve adoption from innovations developed |  |  |  |  | 20000
| 5.7.6. Conference attendance |  | To enable staff disseminate their research and get exposed to cutting edge research | Networking is crucial for scientists | Number of staff attended conferences and papers in proceedings |  |  | 12000 | bar: July 2019 - June 2020 November to July 2019 - June 2020 April
| 5.7.7. Staff internships |  | To equip staff with modern technologies | Science is dynamic as such retooling is critical | Number of staff attended internships |  |  | 15000
| 5.7.8. Support publications |  | To disseminate research findings | Need for users to apply the research | Number of papers published in peer reviewed journals |  |  | 3000
|  | Subtotal | [5 empty] | 126191.67
5.9. ACE action plan for Management and Governance
5.9.1. Establish and operationalize management and leadership of center
|  | 5.9.1.1 1. Support staff salaries (Contribute to gratuity/pension) | To promote efficiency at the centre | Director and deputy director alone cant manage handling all centre issues | Project officer and secretary recruited/pensions accumulated |  |  | 30000
|  | 5.9.1.1.2. Support operations (travel - fuel, communications, stationary and utilities) | To facilitate mobility | For effectivenss, the centre leadership needs to move around meeting stakeholders | Collaborations strengthened |  |  | 10000
|  | 5.9.1.1.3 Procurement (project furniture, project equipment and accessories and office supplies) | For operations of the centre | It is requirement | Staff provided with required resources |  |  | 0 | bar: July 2019 - June 2020 September to July 2019 - June 2020 June
|  | 5.9.1.1.4 Maintenance of the vehicle | To ease mobility | Efficiency needed in mobility | Fit for the road vehicle available |  |  | 14500
|  | 5.9.1.1.5. Facilitate audit | To support audit teams | Ensure accountability | Audit reports |  |  | 9000 | bar: July 2019 - June 2020 October to July 2019 - June 2020 April
| 5.9.2. Conduct Project Steering Committee meetings – ensure regular meetings of all |  | To update steering committee members on progress and decide way forward | Ensure team work | Minutes for PSC meetings |  |  | 22000 | bar: July 2019 - June 2020 September; July 2019 - June 2020 December; July 2019 - June 2020 March; July 2019 - June 2020 June
| 5.9.3. Conduct Technical Committee meetings |  | To strategize on implementation steps together with all members | Ensure team work | Minutes of such meetings |  |  | 16000
| 5.9.4. Conduct National Steering Committee– ensure regular meetings of all |  | To seek approvals at national level | Ensure accountability on how loan funds are spent | Minutes of such meetings |  |  | 13500 | bar: July 2019 - June 2020 October; July 2019 - June 2020 June
| 5.9.5. Support International students and staff Office |  | To facilitate students' welfare | Smooth handling of students' issues ensures smooth learning | International office enhanced |  |  | 8000
| 5.9.7. Supporting Academic Advisory body |  | To support meeting for advisory board | Quality assurance of AquaFish programs | Minutes of meetings and recommendations |  |  | 15000 | bar: July 2019 - June 2020 September; July 2019 - June 2020 March
| 5.9.8. Conduct finance management training |  | To retool finance staff | Ensure upto date staff on finance management skills | well trained staff |  |  | 7740 | bar: July 2019 - June 2020 November; July 2019 - June 2020 June
| 5.9.9. ACE II meetings for peer learning done by RFU |  | To enhance peer learning amongst centres | For effective implementation of ACE II | documentation available |  |  | 35000
| 5.9.10. Coordination and networking |  | To facilitate mobility | For effectivenss, the centre leadership needs to move around meeting stakeholders | Collaborations strengthened |  |  | 34000
| 5.9.18 Train LUANAR management team on management, leadership, communication skills and work ethics | [6 empty] | 10000 | bar: July 2019 - June 2020 October to July 2019 - June 2020 December
|  | Subtotal | [5 empty] | 224740
5.10. ACE action plan for Sustainable Financing
| 5.10.1. Development of short courses |  | To develop short courses to attract funding for sustainance of the AquaFish ACE in the long run | To ensure there are enough resources to continue carrying sustain activities of the ACE | Short courses developed for specific clientelle in the diffent areas /programs covered in the ACE. |  |  | 15000 | bar: July 2019 - June 2020 July to July 2019 - June 2020 November
| 5.10.2. Support faculty to submit grant applications |  | To capacitate staff develop fundable proposals to attract funding to support the center | To attract the extra funding from grants proposals to sustain activities of the center. | Grant proposals funded in various areas and programs within the center addressing different teachinical aspects |  |  | 35000
| 5.10.3. Support institutionalization of the centre to LUANAR |  | To go through the process that will result into AquaFish being institutionalized for sustainability after project phases out | o attract quality staff and students beyond project life |  |  |  | 9000
|  | Subtotal | [5 empty] | 59000
5.11. ACE action plan for Monitoring and Evaluation
| 5.11.1. Guide systematic data collection, analysis, reporting, use and feedback |  | To develop a robust monitoring system that is able to assist in the monitoring of the activities of the center. | To ensure there is systematic data collection, analysis, reporting, use and feedback on the activities being carried out | A monitoring system developed, tested and in use |  |  | 7000 | bar: July 2019 - June 2020 September; July 2019 - June 2020 December; July 2019 - June 2020 March; July 2019 - June 2020 June
| 5.11.2. Mid-term Evaluation |  | To assess project outcomes since project commencement | To enlist success and provide corrective action | Reviewed project strategy for maximizing impact |  |  | 15000 | bar: July 2019 - June 2020 December
|  | Subtotal | [5 empty] | 22000
Contingency
|  | Total Budget | [5 empty] | 2093872.67
Note on I28: USER: Moved from Year 2