## Uses of Funds as per PIM
T
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds (Breakdown)
for the Annual period ending JUNE 2020
(USD )
Expenditure | Semi-Annual Period ending December 2019 |  |  | Cummulative for |  |  | Cummulative since project inception for |  |  | Explanation of | PAD /Life of | Revised
[5 empty] | Financial Year Ending June 2020 |  |  | Financial Year Ending JUNE 2020 |  | Variance | Project | PAD
| Actual US$ | Planned US$ | Variance US$ | Actual US$ | Planned US$ | Variance US$ | Actual US$ | 5 Years Plan US$ | Variance US$
Expenditure Classification as per Project Implementation Plan
5.1.1 PhD program
5.1.1.1 Train 10 National students at PhD level from teaching & learning | 0 | 12000 | 12000 | 49800 | 60000 | 10200 | 66839 | 256080 | 189241 | On going and not all National PhD students have been recruited
5.1.1.2 Train 8 regional students to attend PhD training | 13108 | 12500 | -608 | 15823 | 63000 | 47177 | 24018 | 222204 | 198186 | On going and not all Regional PhD students have been recruited
5.1.1.3 Train 1 full PhD scholarship regional students to attend PhD training | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.1.1 after April 2020 review
5.1.1.4 Train 4 members for partial PhD (research and supervisory) | 0 | 7500 | 7500 | 26045 | 95000 | 68955 | 40620 | 101600 | 60980 | On going
5.1.1.5 Train 24 partial PhD (tuition and supervisory) | 21317.21 | 15000 | -6317.21 | 0 | 15000 | 15000 | 3592 | 64500 | 60908 | On going
Sub Total | 34425.21 | 47000 | 12574.79 | 91668 | 233000 | 141332 | 135069 | 644384 | 509315
5.1.2 MSc Program
5.1.2.1 Train 16 National students at MSc level in teaching & learning | 7202.79 | 75000 | 67797.21 | 82838 | 110334 | 27496 | 103900 | 305522 | 201622 | On going and not all National MSc students have been recruited
5.1.2.2 Send 7 regional students to attend Msc training | 120617.87 | 25000 | -95617.87 | 58936 | 63585 | 4649 | 107791 | 213272 | 105481 | On going
5.1.2.3 Train 2 MScs with full scholarship | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.2.3 after April 2020 review
5.1.2.4 Train Support 49 partial scholarships at MSc level, only research support | 0 | 5000 | 5000 | 59046 | 67000 | 7954 | 102551 | 104800 | 2249 | On going
5.1.2.5 MSc internship | 0 | 15000 | 15000 | 0 | 15000 | 15000 | 120 | 100000 | 99880 | Recruitment of MSc student internship in process but affected by Covid 19
5.1.2.6 Train Support 10 partial scholarships at MSc level, only tuition and supervisory | 110881.11 | 65000 | -45881.11 | 23563 | 65000 | 41437 | 66028 | 358000 | 291972 | On going
5.1.2.7 Support partial scholarship students on stipend (for those of GPA above 3.0) | 10898.8098 | 55000 | 44101.1902 | 15898 | 55000 | 39102 | 45856 | 90000 | 44144 | On going
Sub Total | 249600.5798 | 240000 | -9600.5798 | 240281 | 375919 | 135638 | 426246 | 1171594 | 745348
5.1.3 Resources to support Learning Excellence
5.1.3.1 Send Staff on long-term training at PhD level | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | The funds allocated to this vote have been shifted to 5.1.1.1 after April 2020 review
5.1.3.2 Send 2 regional staff to pursue PHD studies | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | The funds allocated to this vote have been shifted to 5.1.1.2 after April 2020 review
5.1.3.3 Send Staff on long-term training at MSc level | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | The funds allocated to this vote have been shifted to 5.1.2.1 after April 2020 review
5.1.3.4 Send 2 regional staff to pursue Msc studies | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | The funds allocated to this vote have been shifted to 5.1.2.2 after April 2020 review
5.1.3.5 Send 60 Academic &Administrative staff to attend Short courses/ retooling | 29154.73 | 0 | -29154.73 | 78883 | 60800 | -18083 | 225295 | 396600 | 171305 | On going
5.1.3.6. Send 10 Technical staff to attend Short courses/ retooling | 43512.6484 | 0 | -43512.6484 | 43515 | 45500 | 1985 | 115006 | 120000 | 4994 | On going
5.1..3.7 Conduct Short skill enhancement/retooling for both MSc and PhD | 0 | 0 | 0 | 0 | 0 | 0 | 2841 | 50000 | 47159 | on going
5.1.3.8 Organize regional members of Staff exchange visits to teach | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On going
5.1.3.9 Organize National Staff exchange visits to teach | 0 | 0 | 0 | 0 | 50000 | 50000 | 11702 | 20000 | 8298 | On going
5.1.3.10 Organize Staff internship/attachment (to industry) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.1.3.11 Conduct Tracer study | 0 | 0 | 0 |  | 0 | 0 | 20947 | 30000 | 9053 | On going
5.1.3.12 Tendering Process | 0 | 0 | 0 |  | 0 | 0 | 1755 | 2500 | 745 | On going
5.1.3.13 Procure Library resources | 4572.7945 | 10000 | 5427.2055 | 4433 | 15000 | 10567 | 7028 | 22500 | 15472 | More books yet to be procured and the procurement process already intiated
5.1.3.14 Curriculum review for PG programs | 25810.7877 | 35000 | 9189.2123 | 30803 | 75000 | 44197 | 35070 | 90000 | 54930 | On going
5.1.3.15 Organize Retooling course in e-learning and other new teaching methods also experiantial learning | 2591.7955 | 10000 | 7408.2045 | 0 | 36000 | 36000 | 26736 | 40000 | 13264 | On going
5.1.3.16 Develop e-learning materials | 0 |  | 0 |  | 0 | 0 | 0 | 20000 | 20000 | On going
5.1.3.17 Enhance ICT | 6233.5999 | 10000 | 3766.4001 | 7177 | 10000 | 2823 | 15255 | 40000 | 24745 | On going
5.1.3.17 Equipment, chemicals and Supplies | 6359.9003 | 50000 | 43640.0997 |  | 167000 | 167000 | 0 | 173550 | 173550 | Process initiated with procurement office
5.1.3.18 Rehabilitation of Computer Laboratories for 5 Departments | 2954.2901 | 10000 | 7045.7099 | 4073 | 25000 | 20927 | 38740 | 72756 | 34016 | On going
Sub Total | 121190.5463 | 125000 | 3809.4537 | 168884 | 484300 | 315416 | 500375 | 1077906 | 577531
5.2:Research Excellence
5.2.1 Research agenda | 0 | 0 | 0 | 4473 | 50000 | 45527 | 7657 | 15000 | 7343 | On going
5.2.2 PhD Research | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.1.4 after April 2020 review
5.2.3 MSc Research | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.2.4 after April 2020 review
5.2.4 Research for Staff on long term Training PhD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.1.4 after April 2020 review
5.2.5 Research for Staff on long term Training MSc | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.2.4 after April 2020 review
5.2.6 Establish and implement viable MoUs with private or public institutions for applied research | 0 | 0 | 0 |  | 0 | 0 | 4428 | 35000 | 30572 | on going
5.2.7 Staff research grant | 0 | 0 | 0 |  | 0 | 0 | 0 | 60000 | 60000 | Not yet done
5.2.8 Renovate research facilities (ponds, tanks) | 0 | 20000 | 20000 | 10000 | 38670 | 28670 | 20000 | 50000 | 30000 | On going
5.2.9 Scaling up Best Practices | 0 | 0 | 0 |  | 16000 | 16000 | 0 | 32000 | 32000 | Earmarked for 2020/2021 financial year
5.2.10 Publish refereed journal articles | 0 | 5000 | 5000 |  | 8750 | 8750 | 150 | 28500 | 28350 | on going
5.2.11 Dissemination workshops | 0 | 0 | 0 |  | 30000 | 30000 | 0 | 60000 | 60000 | Earmarked for 2020/2021 financial year
5.2.12 Outreach programs | 0 | 0 | 0 |  | 15000 | 15000 | 0 | 30000 | 30000 | Earmarked for 2020/2021 financial year
5.2.13 Scaling up feed mill operations | 0 | 10000 | 10000 |  | 14000 | 14000 | 0 | 10000 | 10000 | Earmarked for 2020/2021 financial year
Su Total | 0 | 35000 | 35000 | 14473 | 172420 | 157947 | 32235 | 320500 | 288265
5.3: Quality Assurance
5.3.1 Curriculum review |  | 0 | 0 |  |  | 0 |  | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.14 after April 2020 review
5.3.2 Monitoring and evaluation |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | The funds allocated to this vote have been shifted to 5.11.1 after April 2020 review
5.3.3 Recruit external examiners |  | 20000 | 20000 |  | 34000 | 34000 | 0 | 44000 | 44000 | Not yet done
5.3.4 Support development of policies (supervision, ethics, etc) | 6352.6027 | 5000 | -1352.6027 | 12726 | 13000 | 274 | 12726 | 10000 | -2726 | On going
5.3.5 Accreditation Regional |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.3.6 after April 2020 review
5.3.6 Accreditation International | 11444.9744 | 30000 | 18555.0256 | 29721 | 70000 | 40279 | 68865 | 115000 | 46135 | On going
5.3.7 Self evaluation |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.3.6 after April 2020 review
5.3.8 Benchmarking (PASET) |  | 0 | 0 | 319 | 15000 | 14681 | 8861 | 20000 | 11139 | Done
5.3.9 Develop an e-based evaluation form and student tracking system |  | 10000 | 10000 | 8618 | 15000 | 6382 | 8618 | 10000 | 1382 | On going
Sub Total | 17797.5771 | 65000 | 47202.4229 | 51384 | 147000 | 95616 | 99070 | 199000 | 99930
5.4: Equity Dimensions
5.4.1 Sensitization meetings on Gender (staff and students) |  | 5000 | 5000 |  | 22500 | 22500 | 0 | 22500 | 22500 | Preparations in progress
5.4.2 Recruit National and Regional students in all programs |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.1.1 and 5.1.2.2 after April 2020 review
5.4.3 Support special scholarships for female candidates at MSc level |  | 20000 | 20000 |  | 46284 | 46284 | 0 | 56284 | 56284 | on going
5.4.4 Support special scholarships for female candidates PhD level |  | 0 | 0 |  | 0 | 0 | 0 | 35130 | 35130 | on going
5.4.5 Special needs students |  | 0 | 0 | 2778 | 0 | -2778 | 2819 | 15000 | 12181 | on going
5.4.6 Recruit National and Regional staff in all programs |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.1.2 and 5.1.2.2 after April 2020 review
5.4. 7 Develop Research Agenda addressing Regional and National Issues |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.2.1 after April 2020 review
5.4.8 Mainstream Gender in the curriculum |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.14 after April 2020 review
5.4. 9 Procure soft infrastructure for all partners |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.17 after April 2020 review
5.4. 10 Encourage Joint research and publications |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.7.9 after April 2020 review
Sub Total | 0 | 25000 | 25000 | 2778 | 68784 | 66006 | 2819 | 128914 | 126095
5.5: Attracting Regional Faculty & Students
5.5.1 Advertise for regional faculty and students | 0 | 500 | 500 |  | 1207 | 1207 | 93 | 2300 | 2207 | On going
5.5.2 Market programs | 6540.3629 | 15000 | 8459.6371 | 8014 | 30000 | 21986 | 14997 | 37500 | 22503 | On going
5.5.3 Develop a framework with partner institutions for reaching potential students and staff in respective countries | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.5.4 Staff mobilization | 0 | 0 | 0 |  | 10000 | 10000 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.5.5 Remedial courses (e.g. language, stats, maths, res methods)-Course material development @ 12,000 and delivery @3000 | 0 | 5000 | 5000 |  | 15000 | 15000 | 0 | 15000 | 15000 | Not yet done
5.5.6 Contributions towards construction of PG Hostel, ACE Offiices & Furniture | [7 empty] | 488086 | 488086 | To commence in 2020/2021 financial year
Sub Total | 6540.3629 | 20500 | 13959.6371 | 8014 | 56207 | 48193 | 15090 | 542886 | 527796
5.6/5.8: National, Regional and International Academic Partners
5.6.1 Support Teaching and learning | 4613.4795 | 20000 | 15386.5205 | 3595 | 0 | -3595 | 3595 | 38000 | 34405 | On going
Advertise for supply of Lab & field supplies for teaching & learning materials |  | 50000 | 50000 | 0 | 102000 | 102000 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.2.4 after April 2020 review
Conduct staff exchange visits | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
Train one staff at MSc level from (MALDECO) | 0 | 15000 | 15000 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.2.1 after April 2020 review
Train one staff at PhD level from (UoE) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.1.2 after April 2020 review
Research facilitation | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.2.4 after April 2020 review
5.6.2 Send 5 staff for Short courses/ retooling | 0 | 20000 | 20000 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.6.3 Create 5 Outreach and technology transfer nodes | 0 | 20000 | 20000 | 5590 | 40000 | 34410 | 5590 | 55000 | 49410 | On going
5.6.4 Send 9 members of staff to attend Conferences | 10859 | 22000 | 11141 |  | 22000 | 22000 | 31944 | 46000 | 14056 | On going
5.6.5 Internship | 0 | 15000 | 15000 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.6.6 Publications | 3300 | 2611 | -689 |  | 2611 | 2611 | 1215 | 24500 | 23285 | On going
Sub Total | 18772.4795 | 164611 | 145838.5205 | 9185 | 166611 | 157426 | 42344 | 163500 | 121156
5.7: National & Regional Sector Partners
5.7.1 Teaching and learning | 395.0425 | 15000 | 14604.9575 | 947 | 17666.67 | 16719.67 | 947 | 35000 | 34053 | Not yet done
5.7.2 Support Staff exchange visits for sector partners | 731.5068 | 20000 | 19268.4932 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.7.3 Research facilitation | 380.5479 | 12000 | 11619.4521 |  | 12025 | 12025 | 18438 | 40000 | 21562 | Not yet done
5.7.4 Short courses/ retooling | 0 | 10000 | 10000 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.7.5 Outreach and technology transfer | 0 | 0 | 0 | 1375 | 20000 | 18625 | 8254 | 90400 | 82146 | On going
5.7.6 Send Sector partners to attend Conferences | 0 | 6000 | 6000 |  | 12000 | 12000 | 10739 | 48000 | 37261 | On going
5.7.7 Facilitate Internships | 0 | 5000 | 5000 |  | 0 | 0 | 0 | 0 | 0 | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.7.8 Short courses | 0 | 0 | 0 |  |  |  | 0 |  |  | The funds allocated to this vote have been shifted to 5.1.3.5 after April 2020 review
5.7.9 Publications | 0 | 3000 | 3000 | 3199 | 3000 | -199 | 5869 | 11500 | 5631 | On going
Sub Total | 1507.0973 | 71000 | 69492.9027 | 5521 | 64691.67 | 59170.67 | 44247 | 224900 | 180653
5.9: Management & Governance
5.9.1 Project Inception Workshop | 0 | 0 | 0 |  |  | 0 | 36646 | 49000 | 12354 | Done
5.9.2 Support Salaries for Coordination Unit Staff | 14632.96 | 15000 | 367.04 | 30625 | 40000 | 9375 | 72604 | 137500 | 64896 | On going
5.9.3 Gratuity & Benefits for Project unit | 2716.8688 | 0 | -2716.8688 | 6377 | 10000 | 3623 | 7224 | 37800 | 30576 | On going
5.9.4 Travel Costs | 4587.9724 | 1500 | -3087.9724 | 8655 | 9000 | 345 | 36729 | 42000 | 5271 | On going
5.9.5 Communication Costs | 1726.0274 | 1000 | -726.0274 | 3347 | 7200 | 3853 | 9823 | 18000 | 8177 | On going
5.9.6 Stationery & Consumables | 3214.124 | 1750 | -1464.124 | 4193 | 3500 | -693 | 12658 | 20000 | 7342 | On going
5.9.7 Utilities | 4838.3683 | 1500 | -3338.3683 | 4691 | 8000 | 3309 | 35598 | 69320 | 33722 | On going
5.9.8 Procure project Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 26656 | 25000 | -1656 | Done
5.9.9 Procure Project Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 21204 | 28700 | 7496 | Done
5.9.10 Office Supplies | 0 | 0 | 0 | 3618 | 5000 | 1382 | 3618 | 7500 | 3882 | On going
5.9.11 Set up & Support International Academic Advisory Board | 0 | 10000 | 10000 | 0 | 5000 | 5000 | 1986 | 2500 | 514 | On going
5.9.12 Hold Annual Steering Commmitte | 0 | 10000 | 10000 | 0 | 12000 | 12000 | 11610 | 110000 | 98390 | On going
5.9. 13 Conduct National Steering committee meetings | 854.3836 | 6000 | 5145.6164 | 2674 | 13500 | 10826 | 8523 | 18000 | 9477 | On going
5.9.14 Hold Project Technical Committee | 14065.1808 | 8000 | -6065.1808 | 23251 | 25000 | 1749 | 51854 | 163525 | 111671 | On going
5.9.15 Support International students office | 0 | 3000 | 3000 | 298 | 8000 | 7702 | 298 | 18500 | 18202 | On going
5.9.16 Procure project vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 57131 | 60000 | 2869 | Done
5.9.17 Maintenance & Vehicle Insurance | 975.8494 | 4500 | 3524.1506 | 1830 | 5500 | 3670 | 5173 | 49500 | 44327 | On going
5.9.18 Train LUANAR management team on management, leadership, communication skills and work ethics | 915.9068 | 10000 | 9084.0932 | 2737 | 10000 | 7263 | 14021 | 20000 | 5979 | On going
5.9.19 Financial management system | 11671.2329 | 7740 | -3931.2329 | 9129 | 7740 | -1389 | 17586 | 23000 | 5414 | On going
5.9.20 ACE II meeting for peer learning | 17801.0959 | 15000 | -2801.0959 | 17285 | 20000 | 2715 | 49318 | 120000 | 70682 | On going
5.9.21 Audit fee | 8783.3315 | 9000 | 216.6685 | 13091 | 9000 | -4091 | 26889 | 45000 | 18111 | On going
5.9.22 Coordination & Networking | 37857.674 | 25000 | -12857.674 | 60083 | 68000 | 7917 | 167294 | 218000 | 50706 | On going
Bank Charges | 3400.5212 | 0 | -3400.5212 | 5000 |  | -5000 | 15422 | 0 | -15422 | Not budgeted for
Sub Total | 128041.4971 | 128990 | 948.5029 | 196884 | 266440 | 69556 | 689865 | 1282845 | 592980
5.10: Sustainable Financing
5.10.1 Conduct Short courses | 0 | 7500 | 7500 | 664 | 15000 | 14336 | 7702 | 40000 | 32298 | On going
5.10.2 Conduct Proposal writing workshop | 8924.7268 | 15000 | 6075.2732 | 10828 | 35000 | 24172 | 14329 | 116300 | 101971 | On going
5.10.3 Support institutionalization | 0 | 4500 | 4500 | 4242 | 9000 | 4758 | 4242 | 15200 | 10958 | On going and was renamed fro support of ODL to Institutionalization of the centre to LUANAR
Sub Total | 8924.7268 | 27000 | 18075.2732 | 15734 | 59000 | 43266 | 26273 | 171500 | 145227
5.11: Monitoring and Evaluation
5.11.1 Conduct Monthly monitoring & evaluation | 1260.274 | 3500 | 2239.726 | 19630 | 7000 | -12630 | 23958 | 38555 | 14597 | On going
5.11.3 Mid term evaluation | 0 | 7500 | 7500 | 0 | 15000 | 15000 | 0 | 15500 | 15500 | Done
5.11.4 End and Impact evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18016 | 18016 | Not yet done as it will be done after project ends
Sub Total | 1260.274 | 11000 | 9739.726 | 19630 | 22000 | 2370 | 23958 | 72071 | 48113
GRAND TOTAL | 588060.3508 | 960101 | 372040.6492 | 824436 | 2116372.67 | 1291936.67 | 2037591 | 6000000 | 3962409

## DLI Statement
Lilongwe University of Agriculture and Natural Resources
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED SDR | AMOUNT ALLOCATED USD$ | AMOUNT DISBURSED SDR | AMOUNT DISBURSED USD$ | UNDISBURSED BALANCE SDR | UNDISBURSED BALANCE USD
DLR 1.1 Signing of the performance and funding agreements and establishing national steering committee | Completion of effectiveness conditions | Done | 425000 | 600000 |  | 594260 | 425000 | 5740
DLR 1.2 Development of the project implementation plan | Detailed implemetation plans for ACE approved by ministry in charge of higher education | Done | 375000 | 500000 |  | 495216 | 375000 | 4784
DLR 2.1 Timely implementation of annual work plans | Timely execution of annual work plan | 80% completed | 375000 | 500000 |  |  | 375000 | 500000
DLR 2.2 Newly enrolled students in the ACE of which at least 20% must be regional African students | Enrol 140 MSc and 32PhD students | Enrolled 73 MSc and 11 PhD students and now awaiting award of scholarships to Semester I Year 2 intake | 850000 | 1200000 |  | 148531.73 | 850000 | 1051468.27
DLR 2.3 Quality accrediatation for education programs | Accreditation at National level submitted to NCHE | Results out and ALL AquaFish programs accredited, now awaiting regional accreditation steps | 425000 | 600000 |  | 300000 | 425000 | 300000
DLR 2.4 partnership for collaboration in applied research and training | To sign 6 MoUs | Signed 8 MoUs and awaiting 6 more | 150000 | 200000 |  | 200000 | 150000 | 0
DLR 2.5 peer reviewed journal papers or peer reviewed conference papers prepared collaboratively with national, regional or international co authors | Publish 10 papers | 20 papers published and others in different stages of publication | 200000 | 300000 |  | 300000 | 200000 | 0
DLR 2.6 Faculty and PHD student exchanges to promote regional research and teaching collaborations | 8 national, 24 regional and 8 international faculty exchanged | 7 faculty, 1 PhD and 6 Technical staff sent, whilst 3 came to LUANAR (1 national and 2 international), awaiting 10 staff from RUFORUM universities | 375000 | 500000 |  | 212000 | 375000 | 288000
DLR 2.7 External revenue generation | Generate $1,400,000 | $400,000 generated and awaits more | 650000 | 900000 |  | 900000 | 650000 | 0
DLR 2.8 institution participating in benchmarking exercise | To enroll for benchmarking under PASET this year 2018 | Waiting for opening by PASET | 75000 | 100000 |  | 100000 | 75000 | 0
DLR 3.1 Timely withdrawal applications supported by interim unaudited financial reports | Internal audit committee produces unaudited financial report | Interim unaudited financial report almost through | 60000 | 75000 |  | 30000 | 60000 | 45000
DLR 3.2 Functioning audit committee | Formation of Internal audit committee and minutes available | In place | 55000 | 75000 |  | 30000 | 55000 | 45000
DLR 3.3 Functioning internal audit unit | Formation of Internal audit committee and minutes available | In place | 55000 | 75000 |  | 30000 | 55000 | 45000
DLR 3.4 Transparency of financial management | Setting up financial management dissemination channels | Once financial report is ready, it will be shared through website | 55000 | 75000 |  | 30000 | 55000 | 45000
DLR 4.1 Timely procurement audit reports | Produce procurement report together with finacial report | Procurement report coming with financial report | 112500 | 150000 |  | 60000 | 112500 | 90000
DLR 4.2 Timely and satisfactory procurement progress report | Postings done on WB site | Posting to be done by February once all procurements are done | 112500 | 150000 |  | 60000 | 112500 | 90000
GRAND TOTAL |  |  | 4350000 | 6000000 | 0 | 3490007.73 | 4350000 | 2509992.27

## EEP Statement
Lilongwe University of Agriculture and Natural Resources
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the annual period ending 30 June 2020
Cummulative for
Eligible Expenditure Program (EEP) | Semi-Annual Period ending December 2019 MK | Semi-Annual Period ending December 2019 US$ | Financial Year End June 30, 2020 MK | Financial Year End June 30, 2020 US$
EEP 1: Salaries | 3475905205 | 4794352.01 | 7237031283 | 9779772.0041
EEP 2: Teaching and laboratory materials | 116693116 | 160956.02 | 129390061 | 174851.4338
EEP 3: Printing and stationery | 93773357 | 129342.5 | 266339998 | 359918.9162
EEP 4: Communation expenses | 58509009 | 80702.08 | 127575983 | 172399.977
EEP 5: Student provisions | 0 | 0 | 9323602 | 12599.4622
EEP 6: Fuels and oils | 51667674 | 71265.76 | 231593783 | 312964.5716
EEP 7: Utilities | 218217932 | 300990.25 | 247983876 | 335113.3459
EEP 8: Insurance | 83435304 | 115083.18 | 83435304 | 112750.4108
EEP 9: Maintenance expenses | 92719243 | 127888.61 | 99936268 | 135049.0108
EEP 10: Training and staff development | 52488865 | 72398.43 | 65923850 | 89086.2838
Total EEPs | 4243409705 | 5852978.84 | 8498534008 | 11484505.4162

## Sources and uses of funds
Lilongwe University of Agriculture and Natural Resources
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Sources and Uses of Funds
for the annual period ending 30 June 2020
Cummulative for
Sources of Fund | Semi-Annual Period ending December 2019 | Financial Year End June 30 2020
| US$ | US$
Opening Cash Balance
Government Funds | 0
World Bank IDA Funds | 2006691 | 2006691
Student Fees
Others | 82910 | 82910
Total | 2089601 | 2089601
Add Receipts
Government Funds
World Bank IDA Funds | 293731.67 | 293732
Student Fees
Others | 176129.04 | 372043
Total Financing | 2559461.71 | 2755376
Less: ACE Expenditure as per Project Implementation Plan
5.1.1 PhD program | 34425.59 | 91668
5.1.2 MSc Program | 249600.5798 | 240281
5.1.3 Resources to support Learning Excellence | 121190.5463 | 168884
5.2:Research Excellence | 0 | 14473
5.3 Quality Assurance | 17797.5771 | 51384
5.4: Equity Dimensions | 0 | 2778
5.5: Attracting Regional Faculty & Students | 6540.3629 | 8014
5.6/5.8: National, Regional and International Academic Partners | 18772.4795 | 9185
5.7: National & Regional Sector Partners | 1507.0973 | 5521
5.9: Management & Governance | 128041.4971 | 196884
5.10: Sustainable Financing | 8924.7268 | 15733
5.11: Monitoring and Evaluation | 1260.274 | 19630
Others | 156431.9239 | 339798
Total Uses of Funds by Components | 744492.6547 | 1164233
Closing Balances | 1814969.0553 | 1591143
Government Funds
World Bank IDA Funds | 1712362 | 1519257
Student Fees | 0 | 0
Others | 102607 | 71886
Total Closing Cash Balance | 1814969 | 1591143